## Sheet1
LIFT EXPENSES AND ACTIONS |  |  |  | 2015-12-12
Phase I – Work Required: |  |  |  | Notes
1 | Sitework for Lift
2 |  | Tree Removal | 2000
3 |  | Concrete Foundation | 8000
4 |  | Dig Trench/Move Electric | 3000
5 |  | Demolition Water Chamber | Excluded | Existing pump box appears active.
6 |  | Grade Lift Area | 2500
7 |  | Relocations & Misc Work | 2000
8
9 | Early Work
10 |  | Oil Tank Removal, Lift Deposit & Professional Fees. | 18500 | Previously Spent.
11
12 | Consultants
13 |  | Land Use Consultants | 10000 | Original estimate increased by P&Z delays
14 |  | Barr Associates | 4000 | Parking Text Amendment & Lift DOB Filings
15 |  | Wetlands Mapping | 800
16 |  | Leonard Surveying | 4000
17 |  | Architect | 2500
18 |  | Town Fees & Applications | 2000
19 | Total |  | 59300
Phase II - Final Phase: |  |  |  | Notes
1 | Lift Installation
2 |  | Install Lift | 15000
3 |  | Paving & walkways | 10000
4 |  | Electric door installed | 2000
5 | Total |  | 27000
| Total Cost Estimate |  | 86300
Notes:
1 | Completion date anticipated in April, 2016. |  |  | Estimated completion prior to P&Z delays.